## marks
2025 Spring 31272 Project Management and the Professional
Group assignment Rubric
Tutorial number / Tutor : | /
Group name: | Group
| Name | Student Id |  | Initials of student | Mark |  | Total marks attempted | Total marks given | Marks given / marks attempted *40 | Mark / 40
Team Member 1: |  | 14480545
Team Member 2: |  | 24822088
Team Member 3: |  | 25127085
Team Member 4: |  | 24482034
Team Member 5: |  | 24827610
Team Member 6: |  | 24555171
Team Member 7: |  | 14172377
Fill inyour initials in the cells of the areas you are responsible for. Also place your initials in the appropriate section 6 item.
Each section will be assigned to one and only one team member and they will receive the marks for that section
Each team member will be responsible for at least one 20 mark section and at least one 10 mark section
SECTION | Details | Max mark | mark | Who |  | Marker's Comment
Section 0 – Exec Summary |  | 10 | 0
Section 1 – Business Overview |  | 10 | 0
Section 2 – Key Project Management Planning and Control Strategies to Adopt
| Stakeholder management | 10 | 0
| Communication plan | 10 | 0
| System development approaches (SDLC) and integration with Project management approach (PLC). | 10 | 0
| Risk management (impact on project only) | 10 | 0
| Project progress monitoring, scope management and change control strategy and governance. | 20 | 0
| Quality management strategy and initial planning | 10 | 0
Section 3 – Major Project Management Activities and Estimates
| High-level tasks of the project (120 – 150 tasks) | 20 | 0 |  |  |  | `
| Task sequencing using activity-on-node (AON) | 20 | 0
| Gantt chart | 20 | 0
| Key project milestones and citical path dependencies | 20 | 0
| Best estimate of time and Validation of proposed budget | 20 | 0
| Human resourcing estimate (to populate task list) | 20 | 0
Section 4 – Conclusion |  | 10 | 0
Section 5 - Slide Pitch (PMP to customer) (Minumum of 4 and a maximum of 10 slides.) | 5 Slide pitch (PMP to customer) | 20 | 0
Section 6 – Additional Criteria: (all) Professionalism, Presentation and Accountability
|  | 10 | 0
|  | 10 | 0
|  | 10 | 0
|  | 10 | 0
|  | 10 | 0
|  | 10 | 0
|  | 10 | 0

## details
Top level | Mark level | Detailed criteria | *Indicative Mark for Content | Total | Given | Total for section
Exec summary |  |  |  | 10 |  | 0
| Executive summary content |  | 5
| Summary of major points |  | 5
Section 1 –Business Overview |  |  |  | 10 |  | 0
| Document introduction, purpose and background |  | 1
| Objectives of the Management System |  | 1
| key success criteria (SMART) |  | 1
| Measurable Organisational Value (MOV) and potential benefits |  | 2
| Specific in-scope and value-added requirements (including traceability); |  | 2
| Out of scope items |  | 1
| Project assumptions |  | 1
| Constraints and dependencies |  | 1
Section 2 – Key Project Management Planning and Control Strategies to Adopt
| Stakeholder management |  |  | 10 |  | 0
|  | Substantiated Stakeholder register (justify why they are in there) | 4
|  | Management of stakeholders is discussed | 4
|  | all stakeholders are categorised appropriately | 2
| Communication plan |  |  | 10 |  | 0
|  | all people in the communication plan are stakeholders | 1
|  | communication needs are discussed | 3
|  | Stakeholder (Recipient), Report Required (Type), Time Due (Frequency), | 3
|  | Produced By (Owner), Delivery Format (Media) | 3
| System development approaches (SDLC) and integration with Project management approach (PLC) |  |  | 10 |  | 0
|  | Development (Waterfall/Agile / other) advantages/disadvantages discussed | 5
|  | Recommendation made; | 3
|  | Rational for recommendation | 2
| Risk management |  |  | 10 |  | 0
(minimum of 15 risks – matches assignment spec)
|  | Risk Management strategy and initial planning | 3
|  | Risks relate to building system | 1
|  | For each known risk give a unique identifier, a task number association (if any), | 6
(risk priority (importance 1 down to 3 based on probability x impact),
description, trigger event, risk owner, probability of it occurring (low/med/high),
potential impact and the strategy to mitigate and manage the risk if it happens)
| Project progress monitoring, scope management and change control strategy |  |  | 20 |  | 0
|  | Governance plan and reporting structure (Steering Committee, PMO etc) | 6
|  | Scope management plan | 6
|  | Project progress monitoring | 4
|  | Variation management strategy | 4
| Quality management strategy and initial planning for same |  |  | 10 |  | 0
(Quality tasks should be included in task list)
|  | Quality plan (for this project) | 4
|  | Quality assurance | 3
|  | Quality control | 3
Section 3 – Major Project Management Activities and Estimates
120-150 tasks are required
| Task list |  |  | 20 |  | 0
|  | Task list contains all project 120 - 150 tasks | 4
|  | Tasks can be traced back to in-scope items | 4
|  | Tasks are related to a plan for building the system | 4
|  | tasks have clear outcomes (deliverables) | 3
|  | Clear task descriptions | 3
|  | Alignment to methodology | 2
| Task sequencing using activity-on-node (AON) |  |  | 20 |  | 0
|  | unifying diagram of all the tasks | 2
|  | includes both task names and task numbers | 2
|  | highlights critical path and float | 2
|  | Forward and Backward pass are complete | 2
|  | Diagram reflects the SDLC and PLC chosen | 2
|  | diagram is readable | 2
|  | diagram follows recognisable standards | 2
|  | All tasks have arrows in and out | 2
|  | obvious beginning / end | 2
|  | Diagrams and task list appear to be consistent | 2
| Gantt Task scheduling on a Gantt chart |  |  | 20 |  | 0
|  | Reflects both the task list and the detailed AON | 4
|  | Gantt is readable and follows recognisable standards | 4
|  | Gantt follows recognisable standards | 2
|  | Milestones and critical path are visible | 4
|  | obvious beginning / end | 2
|  | Gantt reflects the SDLC and PLC chosen | 2
|  | Gantt and task list are consistent | 2
| Key project milestones and critical path dependencies |  |  | 20 |  | 0
at least 8 key milestones
|  | Justify and Discuss - deliverables completed and total expenditure to date | 5
|  | Milestones are reflected in Gantt, AON, Task list | 5
|  | Critical path and milestones are identified | 4
|  | Critical path and Optimisation | 3
|  | How sensitive is the critical path to change? | 3
| Best estimate of time and validation of Budget |  |  | 20 |  | 0
|  | best estimate of time | 3
|  | reasoning for the estimate | 3
|  | Initial ‘top-down’ budget must be realistically allocated to key project phases | 3
|  | A ‘bottom up’ estimate must be given and match the task list | 3
|  | Outcomes of the cross-validation are discussed and recommendations made | 2
|  | (e.g. are there differences? Is initial budget too high/low? | 2
|  | Should a formal request for budget increase/decrease be made? | 2
|  | Discussion on timeline and cost contingencies | 2
| Human resourcing estimate: |  |  | 20 |  | 0
(note: project human resources only – no hardware, software, overhead to be included)
|  | Roles needed | 4
|  | How many people for each role | 4
|  | How long are they needed (days) | 4
|  | Daily charge rate for each role | 2
|  | Reference given for daily charge rate (where did you get it from) | 2
|  | Reflects the task list, AON and Gantt | 4
Section 4 – Conclusion |  |  |  | 10 |  | 0
| Suggested next steps to get the project underway |  | 2
| Relevant approvals required for key project areas |  | 2
| Recommendations |  | 3
| Why choose us (PMP value proposition) |  | 3
Section 5 - Slide deck presentation to the customer |  |  |  | 20 |  | 0
| Slides covering the major points from above |  | 8
| PMP Value proposition |  | 8
| Well-presented and looks professional |  | 2
| Communicates well – structure, language, word choice |  | 2
The assignment brief states approx 5 slides.
We are expecting a minumum of 4 and a maximum of 10 slides
Section 6 – Additional Criteria – Professionalism, Presentation and Accountability |  |  |  | 10 | (each) | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Well-presented and looks professional |  | 2
| Appropriate title page (with student names/numbers plus tutor name |  | 1
| Table of contents |  | 2
| Communicates well – structure, language, word choice |  | 2
| Conforms to UTS Style Guide (page 2 of the FEIT cover sheet) |  | 1
| Performed their assigned role |  | 2
*Indicative
For example, the marker may want to award marks for orginality